## OP120
PLANNING 2024_0502
WEEKS FROM ORDER
LIST OF ACTIVITIES | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
SURVEYS |  | X
MECHANICAL PROJECT |  |  | X | X | X | X
ELECTRICAL PROJECT |  |  |  | X | X
SOFTWARE PROJECT |  |  |  |  | X
PURCHASES OF MATERIALS |  |  |  | X | X | X | X | X | X | X | X
MECHANICAL CONSTRUCTION | [10 empty] | X | X | X | X | X | X
ASSEMBLIES | [16 empty] | X | X
COMMISSIONING | [17 empty] | X | X
ASSISTANCE | [18 empty] | X | X
COURSE | [19 empty] | X